## Sheet1
ID | Risk Description | Likelihood | Impact | Mitigation Strategy | Owner
1 | Data loss during migration | Medium | High | Perform backups before migration | IT Lead
2 | Low employee adoption | Medium | Medium | Conduct mandatory training sessions | PM
3 | Vendor delivery delays | Low | High | Include penalty clauses in vendor contract | PM